## Sheet1
Stage | Task | Planned Output | Status | Evidence/File | Notes/Reflection
1 | Project planning and dataset selection | Project scope and selected dataset | Completed
2 | Project workspace setup | Organised project folders | Completed
3 | Raw data inspection | Data quality and structure assessment | Completed | 04_Python_Analysis/01_Data_Inspection.ipynb | Initial inspection identified missing values, geolocation duplicates, multiple customer IDs, incomplete order statuses and an incomplete time range. These findings will guide the cleaning and preparation decisions.
4 | Data cleaning and preparation | Cleaned datasets | Completed | 04_Python_Analysis/02_Data_Cleaning.ipynb; 02_Cleaned_Data | Data was cleaned using analysis-specific decisions rather than blanket deletion or imputation. Delivered transactions were prepared for sales analysis, product categories and geolocation data were standardised, and one-to-many relationships were validated to prevent duplicated records and financial values. Six prepared datasets were exported for further analysis.
5 | SQL database development | Database and SQL queries | Completed | 03_SQL/01_Database_Setup.sql; 03_SQL/02_Load_Data.py; 03_SQL/03_Validation_Queries.sql; 03_SQL/04_Validate_Database.py; 03_SQL/05_Analysis_Queries.sql; 03_SQL/retail_analytics.db | A relational SQLite database was developed using primary and foreign keys to preserve relationships between customers, orders, products, sellers, payments and order items. Record counts, foreign-key integrity and delivered sales were validated against the Python preparation results. SQL analysis identified sales, product and customer patterns. Only 3.0% of customers with delivered orders were repeat customers, which will be considered when selecting the customer segmentation method.
6 | Exploratory Data Analysis | Sales/customer insights and visualisations | Completed | 04_Python_Analysis/03_Exploratory_Data_Analysis.ipynb | EDA identified temporal, product, customer, geographical and order-level patterns. Sales increased across the main observation period, while early 2016 data was sparse. Customer spending was right-skewed and only 3% of customers made repeat purchases. These findings will inform the selection of customer segmentation and forecasting methods.
7 | Customer analytics and segmentation | Customer groups and evaluation | Completed | 04_Python_Analysis/04_Customer_Segmentation.ipynb; 02_Cleaned_Data/customer_segments.csv | Customer segmentation was developed using recency, log-transformed monetary value and items purchased. Four K-Means segments were selected using the elbow method, silhouette analysis and business interpretability. The two-cluster solution had stronger statistical separation, but four clusters provided more useful customer profiles. Frequency was not used as a clustering feature because 97% of customers made only one delivered order. The final output contains 93,358 unique customers with no missing segment assignments.
8 | Sales forecasting | Forecasting models and model comparison | Completed | 04_Python_Analysis/05_Sales_Forecasting.ipynb; 02_Cleaned_Data/weekly_sales_forecast.csv | Weekly sales were modelled using a chronological 12-week test period. Five forecasting approaches were compared. Holt trend achieved the strongest overall test performance with MAE 36,708.38, RMSE 43,930.28 and MAPE 19.77%, reducing RMSE by 13.34% compared with the naive benchmark. The model was refitted using 85 complete weeks and a 12-week planning forecast was exported for Power BI. Short-term variation and the limited historical series remain important forecasting limitations.
9 | Power BI dashboard development | Interactive dashboard | Completed | 05_PowerBI/Retail_Sales_Analytics_Dashboard.pbix; 06_Design/Power_BI_Dashboard_Design.docx; 06_Design/Power_BI_Dashboard_Wireframes.pptx | A four-page Power BI dashboard was developed to present executive KPIs, sales analysis, customer segmentation and sales forecasting. Interactive slicers and DAX measures were used to support business analysis. The dashboard was designed for clear navigation and interpretation, although further usability testing with business users would improve its practical evaluation.
10 | Artefact testing | Test cases, expected/actual results | Completed | 07_Testing/PowerBI_Testing_Results.docx; 07_Testing/Test_01_Executive_Overview.png; 07_Testing/Test_02_Customer_Segment_Filter.png; 07_Testing/Test_03_State_Filter.png; 07_Testing/Test_04_Customer_Segmentation.png; 07_Testing/Test_05_Sales_Forecasting.png | Five functional tests were completed to check dashboard calculations, customer segment filtering, geographical filtering, segmentation results and forecasting visualisations. Expected and actual outcomes were documented with screenshots. All five tests passed, although testing was limited to selected functions and did not include external user testing.
11 | Artefact evaluation | Evaluation against objectives | Completed | 04_Python_Analysis/04_Customer_Segmentation.ipynb; 04_Python_Analysis/05_Sales_Forecasting.ipynb; 07_Testing/PowerBI_Testing_Results.docx Copy | The artefact was evaluated against the project objectives and analytical results. Four K-Means customer segments were selected for business interpretability, although the two-cluster solution achieved a stronger silhouette score. Holt's linear trend produced the lowest forecasting error among the five evaluated methods, with MAE of R$36,708.38 and MAPE of 19.77%. The solution achieved its main technical objectives, but historical data limitations and the absence of external user testing restrict its operational validation.
12 | Report completion | Final MSc project report | Completed | Final MSc Project Report.docx — submitted separately through Turnitin | The final MSc project report was completed and submitted through Turnitin. It documents the research background, project methodology, system design, implementation, testing, evaluation and findings. The report also discusses limitations and recommendations for future development. The writing process helped consolidate the technical work and critically evaluate the extent to which the project objectives were achieved.
13 | Artefact preparation | Final submission ZIP and demonstration | In Progress | Retail_Sales_Forecasting_Project/ — artefact folders under final review; submission ZIP pending | The project files are being reviewed and organised for the final artefact submission. Python notebooks, cleaned datasets, SQL scripts, the SQLite database, Power BI dashboard, design documentation and testing evidence have been identified. The remaining tasks are to verify the original data files, prepare the README documentation, check the working artefact and create the submission ZIP. This stage remains in progress until the final package has been checked and submitted.